# Purpose and Scope

This plan covers change management for the Meridian S/4HANA rollout across Finance, Procurement and Logistics. It is reviewed weekly at the Thursday cadence.

# Stakeholder Engagement

Change network stands at 16 named champions across 6 sites. Porto has appointed a champion; all sites are now covered.

# Communications

Wave 1 go-live comms approved by the sponsor. Intranet hub is live. First countdown mailer scheduled for 1 September.

# Risks and Issues

Logistics super-user availability is now escalated to the steering committee after the Ops director declined to backfill during peak season. A second risk has opened on master data readiness following the Week 12 data audit.

# Activity Schedule

| Activity ID | Activity | Owner | Status | Due Date |
| --- | --- | --- | --- | --- |
| CM-01 | Change impact assessment - Finance | R. Iyer | Complete | 2026-07-31 |
| CM-02 | Change impact assessment - Logistics | R. Iyer | Complete | 2026-08-21 |
| CM-03 | Champion network stand-up | S. Brandt | Complete | 2026-08-28 |
| CM-04 | Go-live comms pack | L. Haddad | In Progress | 2026-09-11 |
| CM-05 | Training needs analysis - Wave 2 | R. Iyer | In Progress | 2026-09-18 |
| CM-06 | Master data readiness remediation | G. Novak | Not Started | 2026-09-25 |