## Wave 1 Completion
Employee | Role | Course | Status | Completion % | Due Date
A. Okafor | AP Clerk | S4 Finance Core | In Progress | 40 | 2026-09-04
B. Lindqvist | AP Clerk | S4 Finance Core | Not Started | 0 | 2026-09-04
C. Moreau | Buyer | S4 Procurement | Completed | 100 | 2026-08-28
D. Ferreira | Buyer | S4 Procurement | In Progress | 60 | 2026-08-28
E. Tanaka | Warehouse Lead | S4 Logistics | Not Started | 0 | 2026-09-11
F. Adeyemi | Warehouse Lead | S4 Logistics | Not Started | 0 | 2026-09-11
G. Novak | Master Data | Data Stewardship | In Progress | 75 | 2026-08-21